## Table 2
SITE ADDRESS: Chandanwadi, Marine Lines, Mumbai |  |  |  |  | Expected Weather Condition:
VALENCIA & MISHAL VENTURES PVT. LTD.
Rev No : 00
Day & Date of Report: Tuesday, 16 January, 2024 |  |  |  |  | Name of Project: One Marina - Sale Tower & Rehab Building
SITE MANPOWER STRENGTH IN (RCC WORK) |  |  |  |  | MAJOR PLANTS/ EQUIPMENTS |  | CIL PROJECT STAFF
Sr. No. | Contractor | Category / Tradesman | REHAB Blg. | SALE TOWER | Item Descriptions | Qty. | Designation | Nos.
[5 empty] | Tower Crane | 2 | Project Incharge | 1
1 | CIL | Foreman | 8 | 14 | Concrete Pump | 1 | Sale - Tower Incharge | 1
2 | CIL | Carpenters | 40 | 39 | Bar Bending Machine | 4 | Rehab - Tower Incharge | 1
3 | CIL | Riggers | 9 | 8 | Bar Cutting Machine | 4 | Planning | 1
4 | CIL | Steel Fitters | 7 | 30 | Curing & Dewat. Pump | 6 | Billing | 2
5 | CIL | Threading Operators | 0 | 2 | Water Tank | 6 | (QA/QC) | 5
6 | CIL | Mason + Grinders | 13 | 5 | Power floaters | 2 | Engineers (Sale Tower) | 2
7 | CIL | Block Work Team | 6 |  | Concrete Vibratory | 7 | Engineers (Rehab Tower) | 2
8 | CIL | Gypsum Work |  |  | Wheel Barrows | 10 | Surveyor | 2
9 | CIL | Unskilled Labours | 25 | 12 | Wood Cutting Machine | 2 | Supervisor +Foreman | 19
10 | CIL | Crane/Passenger Hoist Opt. | 3 | 2 | T.S(Total Station) & Auto Level | 5 | P&M | 2
11 | CIL | Signal man | 3 | 3 | Cube Testing Machine | 1 | Safety | 5
12 | CIL | Welders/ Fabricators | 7 | 2 | Cube Moulds | 40 | Store | 2
13 | CIL | Electricians | 2 | 1 | Passenger hoist | 2 | Admin | 3
14 | CIL | Plumbers | 1 | 1 | Compressor | 1
15 | CIL | Conc. Pump Operator | 1 | 1 | Threading & Throwsing Machine | 2
16 | CIL | Conc. Pump Gang Members | 5 | 5
TOTALS |  |  | 130 | 125 | TOTAL | 95 | TOTAL | 48
GRAND TOTAL |  |  | 255
MATERIAL STATUS
REINFORCEMENT STEEL |  |  |  |  | CONCRETE
Sr. No. | Bar Dia. | Qty.Till date | Stock Qty. | Unit | Concrete Grade | Unit | Quantity Till date | Yesterday's Qty.
1 | 08mm | 439.35 | 7.268 | MT | M7.5 | M3 | 1231.75
2 | 10mm | 585.81 | 0.896 | MT | M10 | M3 | 1094
3 | 12mm | 664.72 | 2.487 | MT | M15 | M3 | 1410
4 | 16mm | 297.44 | 2.046 | MT | M20 & M25 | M3 | 65.5
5 | 20mm | 405.59 | 11.259 | MT | M30 & M40 | M3 | 1323
6 | 25mm | 566.62 | 7.106 | MT | M45 & M45 RAFT | M3 | 7712
7 | 32mm | 817.89 | 0 | MT | M50 | M3 | 6094.5
8 |  |  |  |  | M60 | M3 | 7062.75 | 46.25
9 |  |  |  |  | M70 & M70-SCC | M3 | 2863.5 | 3
TOTAL = |  | 3777.4 | 31.062 | MT | TOTAL = | M3 | 28857 | 49.25
WORKS PLANNED FOR TODAY
REHAB BUILDING
# SHUTTERING WORKS: - 20th floor Pour-1 & 2 shuttering; 19th floor lift area shuttering Pour-3
# REINFORCEMENT STEEL WORK: 20th Floor Pour-1 & 2
# CONCRETE WORKS:
# MISCELLANEOUS OTHERS: (1) Post pour repairs (2) AAC Block work 11th & 13th floor (3) Housekeeping work Of Required Areas (4) Curing (5) Safety screeen jumping
NON-TOWER AREA
# SHUTTERING WORKS: B1 Beam & Slab Shuttering.
# REINFORCEMENT STEEL WORKS:B1 Slab & Beam binding Reinforcement
# CONCRETE WORKS:
# Misc. Other Work : Dewatering & Housekeeping work Of Required Areas,Post pour work for RW
SALE TOWER
# SHUTTERING WORKS: P1 to P2 C34,C37,C40,ST 02 P2 to P3 C17,C4,C18;Pour-3 Starter making & Fixing
# REINFORCEMENT STEEL WORKS: P1 to P2 ST2,Column C44,P2 to P3 Column C21,C9,C39,C6,C30A,B
# CONCRETE WORKS: P1 TO P2 C37,P2 TO P3 C17,C25;P1 to P2 ST1
# MISCELLANEOUS OTHERS: Post pour works at Ground floor.
WORKDONE YESTERDAY
REHAB BUILDING
# SHUTTERING WORKS: - 20th floor Pour-1 & 2 shuttering; 19th floor lift area shuttering Pour-3
# REINFORCEMENT STEEL WORK: 20th Floor Pour-1 & 2
# CONCRETE WORKS:
# MISCELLANEOUS OTHERS: (1) Post pour repairs (2) AAC Block work 10th & 12th floor (3) Housekeeping work Of Required Areas (4) Curing (5) Safety screeen jumping
NON-TOWER AREA
# SHUTTERING WORKS: B1 Beam & Slab Shuttering.
# REINFORCEMENT STEEL WORKS:B1 Slab & Beam binding Reinforcement
# CONCRETE WORKS:
# Misc. Other Work : Dewatering & Housekeeping work Of Required Areas,Post pour work for RW
SALE TOWER
# SHUTTERING WORKS: P1 to P2 ST1, ST2 column C37,C34, C40 ;P2 to P3 Column C4, C18, C25, C9.
# REINFORCEMENT STEEL WORKS: P1 to P2 ST1, ST2Column C44,P2 to P3 Column C6, C30 A,B, C9, C21.
# CONCRETE WORKS: P2 to P3 Column C17, C25, C37, P1 to P2 ST1.
# MISCELLANEOUS OTHERS: Post pour works at Ground floor.
AREA OF CONCERN AFFECTING PROGRESS OF WORKS | [6 empty] | REMARKS
32mm & 10mm steel is not available at site. No workfront for fitters.
PREPARED BY: Suyog Shrirao |  |  |  |  | CHECKED BY: Mr. Sumith S
DESIGNATION: Engineer - Planning |  |  |  |  | DESIGNATION: General Manager

## Sheet1
Sr. No. | Contractor | Category / Tradesman | SALE TOWER | Item Descriptions | Qty. | Designation | Nos.
1 | CAPACITE INFRA | Foreman | 14 | Tower Crane | 2 | Project Incharge | 1
2 | CAPACITE INFRA | Carpenters | 39 | Concrete Pump | 1 | Sale - Tower Incharge | 1
3 | CAPACITE INFRA | Riggers | 8 | Bar Bending Machine | 4 | Rehab - Tower Incharge | 1
4 | CAPACITE INFRA | Steel Fitters | 30 | Bar Cutting Machine | 4 | Planning | 1
5 | CAPACITE INFRA | Threading Operators | 2 | Curing & Dewat. Pump | 6 | Billing | 2
6 | CAPACITE INFRA | Mason + Grinders | 5 | Water Tank | 6 | (QA/QC) | 5
7 | CAPACITE INFRA | Block Work Team |  | Power floaters | 2 | Engineers (Sale Tower) | 2
8 | CAPACITE INFRA | Gypsum Work |  | Concrete Vibratory | 7 | Engineers (Rehab Tower) | 2
9 | CAPACITE INFRA | Unskilled Labours | 12 | Wheel Barrows | 10 | Surveyor | 2
10 | CAPACITE INFRA | Crane/Passenger Hoist Opt. | 2 | Wood Cutting Machine | 2 | Supervisor +Foreman | 19
11 | CAPACITE INFRA | Signal man | 3 | T.S(Total Station) & Auto Level | 5 | P&M | 2
12 | CAPACITE INFRA | Welders/ Fabricators | 2 | Cube Testing Machine | 1 | Safety | 5
13 | CAPACITE INFRA | Electricians | 1 | Cube Moulds | 40 | Store | 2
14 | CAPACITE INFRA | Plumbers | 1 | Passenger hoist | 2 | Admin | 3
15 | CAPACITE INFRA | Conc. Pump Operator | 1 | Compressor | 1
16 | CAPACITE INFRA | Conc. Pump Gang Members | 5 | Threading & Throwsing Machine | 2

## Sheet2
Sr. No. | Bar Dia. | Qty.Till date | Stock Qty. | Unit | Concrete Grade | Unit | Quantity Till date | Yesterday's Qty.
1 | 08mm | 439.35 | 7.268 | MT | M7.5 | M3 | 1231.75
2 | 10mm | 585.81 | 0.896 | MT | M10 | M3 | 1094
3 | 12mm | 664.72 | 2.487 | MT | M15 | M3 | 1410
4 | 16mm | 297.44 | 2.046 | MT | M20 & M25 | M3 | 65.5
5 | 20mm | 405.59 | 11.259 | MT | M30 & M40 | M3 | 1323
6 | 25mm | 566.62 | 7.106 | MT | M45 & M45 RAFT | M3 | 7712
7 | 32mm | 817.89 | 0 | MT | M50 | M3 | 6094.5
8 |  |  |  |  | M60 | M3 | 7062.75 | 46.25
9 |  |  |  |  | M70 & M70-SCC | M3 | 2863.5 | 3

## Sheet3
Floor | Pour | Work Done | Status
Podium 2 |  | # SHUTTERING WORKS - P1 to P2 ST1, ST2 column C37,C34, C40 ;P2 to P3 Column C4, C18, C25, C9. | Inprogress
Podium 3 |  | # SHUTTERING WORKS - P1 to P2 ST1, ST2 column C37,C34, C40 ;P2 to P3 Column C4, C18, C25, C9. | Inprogress
Podium 1 |  | # SHUTTERING WORKS - P1 to P2 ST1, ST2 column C37,C34, C40 ;P2 to P3 Column C4, C18, C25, C9. | Inprogress
Podium 1 |  | # REINFORCEMENT STEEL WORKS - P1 to P2 ST1, ST2Column C44,P2 to P3 Column C6, C30 A,B, C9, C21. | Inprogress
Podium 2 |  | # REINFORCEMENT STEEL WORKS - P1 to P2 ST1, ST2Column C44,P2 to P3 Column C6, C30 A,B, C9, C21. | Inprogress
Podium 3 |  | # REINFORCEMENT STEEL WORKS - P1 to P2 ST1, ST2Column C44,P2 to P3 Column C6, C30 A,B, C9, C21. | Inprogress
Podium 2 |  | # CONCRETE WORKS - P2 to P3 Column C17, C25, C37, P1 to P2 ST1. | Inprogress
Podium 3 |  | # CONCRETE WORKS - P2 to P3 Column C17, C25, C37, P1 to P2 ST1. | Inprogress
Podium 1 |  | # CONCRETE WORKS - P2 to P3 Column C17, C25, C37, P1 to P2 ST1. | Inprogress
Ground |  | # MISCELLANEOUS OTHERS - Post pour works at Ground floor. | Inprogress